## Step1&2
Step 1 (App startup and Authentication) |  | Step 2 (Inside the app)
Features to Implement | Time | Features to Implement | Time
Detecting in which country the user is (IP address + App Localization) and displaying the appropriate welcome page, Visual info |  | Implement CMS loading functionalities for the home page, and other pages
Implementing facebook signin (Only outside Africa) |  | Implement Editorial navigation when the user clicks on editorial caroussel content
Implementing email/password signin |  | Implement selection navigation and loading when the user Clicks on a selection title
Implementing password recovery |  | Implement in app purchases when the user isn't subscribed
Implemeting facebook signup (Only outside Africa) |  | Implement some sort of HTML parsing for product description To make it more readable for the user, (with our fonts and without the html liks if there are broken links)
Implementing Apple Signin/Signup (Apple Native Auth Flow) (Only outside Africa) |  | Implement FAQ url navigations, and implement mailing to the Youscribe team if the user needs to.
Make a background service to Send user information to server at startup - Sending Favorites, Last Readings, Offline List, Bookmarks to the server and receiving these items too. - Sending init data as (Firebase token to API) |  | Implement product read progress bar, that displays how much of the book the user has read
Detecting if the user is subscribed or not. |  | Implement the browse functionality
Add local storage solution (Most likely SQLite) |  | Implement theme search and sort
When user tries to signup from a country with (Orange co branding) available in that country, we display a popup stopping the user from signin in, and we ask to perform a digital virgo sigup (The message is returned by the mobile API) |  | Implement infinite scroll
Styling the application
Making a great architecture, in such a way that the app can be duplicated easily
Making a robust analytics and logging system (Just like the one in Youscribe)
Implement the UI structure for the app (Pages, Tabs, menus etc)
Adding external fonts and using them (Like Font Awesome)
| 0 |  | 0

## Step3&4
Step 3 (Implement The Reading features) |  | Step 4 (Offline Functionalities)
Features to Implement | Time | Features to Implement | Time
Implement the downloads functionality |  | Implement caches in local database for Home page, Fav, offline, last reading.
Implement the file system logic (Read/Write) Delete get product file path etc |  | Implement Cache first data queries in viewmodels when not internet is available.
Implement The service that cleans downloaded books when rights expire. |  | Implement Empty views for each pages
Implement Audio Reader functionalities. |  | Implement No connection views when needed. (Browse page etc)
Implement PDF reader functionalities |  | Implement guards for actions that can’t be performed offline
Implement epub reader functionalities |  | Implement offline (Favorite additions, Favorite removal, Last readings addition)
Implement local book marks |  | Implement Favorite, Last reading sync at startup
Implement bookmark syncronisation with APIs |  | Implementing Google play and Apple Subscriptions
Implement password encryption on iOS and Android
Implement an epub reader
| 0 |  | 0

## Step5&6
Step 5 (Co-branding and CI/CD, Push Notifications) |  | Step 6 (Tests and Additional Improvements)
Features to implement | Time (Days) | Column1 | Column2
Add Firebase push notifications functionalities |  | Add play back controls on app's home page Just as spotify.
Implement The most crucial scenarios (Open URL & Open page first) |  | Deploy the app for internal tests
Create prod and beta scripts for CI/CD |  | Iterate through reports and corrections
Create a cobrand for canal + (With dynamic colors) |  | Firebase Push notifications should be made separately And you should make it dynamic for the addition of new firbase brands
Implement getting firebase notification KPIs
An alternative for firebase dynamic links
Implement timed tasks (Tasks that run in a timely fashion)
Implement the selections functionality
Implementing search and classification handeling
0